## project-high-level-pl
Best practise managment
Type | Name | Owner | Main Effort | Timeline - Start | Timeline - End | revised: | Aug | Sept |  |  | Oct |  | Nov |  | Dec |  | Jan | Feb |  | Mar | Apr | May | Jun | Jul
Paid | Paid Work - programmer | Sanjay | Klaus | ongoing
Paid | Paid Work - programmer | Sanjay | Ceasar | ongoing
Paid | Paid Work - programmer | Sanjay | Jun | ongoing
Paid | Paid Work - programmer | Sanjay | Bruce | ongoing
Product | Ongoing - Maintanence, development? | Jim Griffiths | Ivan | ongoing
[7 empty] | Aug | Sept |  |  | Oct |  | Nov |  | Dec |  | Jan | Feb |  | Mar | Apr | May | Jun | Jul
Product | streamSWEET product development process | Jim Griffiths | Jim | 2018-08-27 | 2018-09-14 | 2018-12-15
Deployment | Improve deployment process | Steve | Steve | 2018-08-27 | 2018-09-14 | 2018-12-15 | [9 empty] | Ongoing?
Product | Actual Development | Jim Griffiths | Klaus
Sales/marketing | Sales and marketing plan | Steve | Steve | 2018-08-27 | 2018-09-27 | [8 empty] | Done
Sales/marketing | Social networking schedule | Steve | Steve | 2018-09-27 | 2018-09-27 |  |  |  |  | Done
Sales/marketing | Product fit for market - what? | Steve | Steve | 2018-09-27 | 2018-12-15 | 2019-01-15
Sales/marketing | How to build customer relationships best | Steve | Steve | 2018-09-22 | 2018-09-22 | 2018-12-15 | [9 empty] | Done
Technical | Upgrade platform to latest environ | Bruce | Ivan | 2018-09-15 | 2018-10-22 | [6 empty] | Done
Technical | Identify and apply programming standards | Bruce | Ivan | 2018-09-01 | 2018-12-01 | [13 empty] | WIP
Technical | Establish documentation | Bruce | Team | 2018-08-27 | 2018-12-23 | [13 empty] | WIP
Technical | Migrate streamSWEET to .NET Core 2 / MVC | Bruce | Ivan | 2019-01-01 | 2019-09-08
Sales/marketing | CIL Support Strategy | Bruce | Bruce | 2018-08-27 | 2018-09-03 |  |  |  | Not Doing
Technical | Establish proven backup / recovery processes | Bruce | TBA | 2018-10-17 | 2018-11-19 | [8 empty] | ??
Deployment | New job system | Bruce | Bruce | 2018-10-16 | 2018-12-23 | 2019-02-15
Technical | CSS Review | Bruce/Jim???
[7 empty] | Aug | Sept |  |  | Oct |  | Nov |  | Dec |  | Jan | Feb |  | Mar | Apr | May | Jun | Jul
Note on A1: steve: Our management defines how we achieve the goals and priorities identified within this strategy paper. The overall intent is to a lower the number of things worked on at once, but in more planned, structured, and team orientated way that can ensure a quality outcome.
Note on B11: steve: Determine streamSWEET Development Version update Process
Note on B12: steve: Effective deployment is critical - it reflects on us as a business and is seen every day by current and new customers. We need to establish a process that is rigid enough to allow the management outcomes below, without hindering flexibility required to complete any job in a timely fashion.
Note on B14: steve: Write a Sales and Marketing Plan
Note on B16: steve: Make a product fit for the Market
Note on B18: steve: There is an increasing gap between standard functionality which is expected, and that which our current platforms deliver. Microsoft has recently made it clear that our current platform will continue to be supported, but will not have further development invested to it. We are able to take advantage of many updates on our current version and eke it out for a while further yet.
Note on B19: steve: Lots of time is wasted as programmers apply personal styles. This often means old mistakes are remade, working with other’s code takes time to figure before addressing business issues, etc. Programming code becomes massively more efficient when 100% consistency is applied.
Note on B20: steve: write a documentation plan and impliment it.
Note on B21: steve: The current streamSWEET system runs on the ASP.NET Web Forms application platform. This platform appears to be entering the twilight of its relevant life, with ASP.NET Core becoming the preferred option. Migrating to the new platform will be a significant project.
Note on B22: steve: CIL dependency is too high (50%)and relies on Bruce as the main person driving this customer relationship. CIL revenue is critical to the business, and Bruce’s relationship is currently critical to supply of that service. It is prudent to build secession and quality delivery around this clients business activity.
Note on B23: steve: Stream’s server environment continues to evolve. Basic backups are running, however we don’t have a comprehensive and clean recovery process that has been fully proven to work seamlessly. This plan needs to include workstations, office servers and live servers.
Note on B24: steve: There are plans to replace the current job system. This will support a much leaner tech and spec process and improved job management. This may be a now job, or something to work towards over time, requiring small improvements to deployment process in the short term.

## Sheet1
2018-08-27 | 2018-09-14
2018-04-09 | 2018-04-09
2019-08-01 | 2019-09-08
2018-08-27 | 2018-09-27
2018-09-27 | 2018-10-27
2018-09-27 | 2018-06-12
2018-03-09 | 2018-03-09
2018-08-27 | 2018-07-10
2018-09-22 | 2018-10-22
2018-08-27 | 2018-12-24
2018-10-18 | 2019-09-08
2018-08-27 | 2018-09-03
2018-10-17 | 2018-11-19
2018-10-16 | 2018-12-23